## CRED Tables
Cost Risk/Uncertainty Exposure Determination (CRED) Model
Note: | Each attribute in the material information category is explained in the Definitions tab
Attributes in each Material Information Category can be tailored out match the cost environment
Based on the work of John McGarry, ARDEC. & Dr. Robert Charette, ITABHI Corp
Software Sustainment Cost Environment
Operations and Sustainment | 1.0 Software Change Product | 3.0 Software Licenses | 4.0 C&A | 5.0 System Facilities | 6.0 Sustaining Engineering | 7.0 Field Software Engineering | 8. Other Costs | Sum
What Should We Know? | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 30
What Do We Know? | 10 | 5 | 8 | 0 | 0 | 0 | 0
Individual Exposure | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 7
[7 empty] | Category Exposure | 0.23333
Software Internal Attributes
Operations and Sustainment | Number Of External Interfaces | Execution Timing Constraints | COTS Product Incorporation | Critical Technology | Data Rights | Sum
What Should We Know? | 10 | 10 | 10 | 10 | 10 | 50
What Do We Know? | 10 | 8 | 5 | 0 | 0
Individual Exposure | 0 | 2 | 5 | 10 | 10 | 27
[5 empty] | Category Exposure | 0.54
Program / Project Management Attributes
Operations and Sustainment | Management Personal Capability | Technical Personal Capability | Technical Process Capability | Facilities & Infrastructure Support | Sustainment / Funding Rhythm | Project & Program Management | Sum
What Should We Know? | 10 | 10 | 10 | 0 | 0 | 0 | 30
What Do We Know? | 8 | 10 | 0 | 0 | 0 | 0
Individual Exposure | 2 | 0 | 10 | 0 | 0 | 0 | 12
[6 empty] | Category Exposure | 0.4
External Program Environment Attributes
Operations and Sustainment | External Stakeholders | Mandates | Policy-driven Sustainment / Funding Rhythm | Sum
What Should We Know? | 10 | 10 | 10 | 30
What Do We Know? | 10 | 10 | 2
Individual Exposure | 0 | 0 | 8 | 8
|  |  | Category Exposure | 0.26667
Sum of all Individual Exposures | 54
Sum of Should-We-Know | 140
Total Exposure | 0.38571

## Definitions
Source: Jones, Cheryl, et al, “The Cost Risk/Uncertainty Exposure Determination (CRED) Model – A New Approach, ICEAA 2024 Professional Workshop
Material Information Category | Attributes | Definitions
Software Sustainment Cost Environment | 1.0 Software Change Product | This attribute addresses what is known about the amount of anticipated change to the software. The volume of changes could be expressed using several different measures: number of requirements, number of function points, number of RICE-FW objects, number of external interfaces, number of software change requests, number of source lines of code, etc. Is the amount of change known for this estimate?
| 3.0 Software Licenses | Are the number and cost of each Commercial Off The Shelf (COTS) product used in development and operations known? Which products are renewed annually? If the software does not use COTS (or other types of Non-Developed Items), this attribute would not be considered.
| 4.0 C&A | Certifications and Accreditations (C&A). Will the software have to be certified or accredited for things such as security, safety, networthiness, or airworthiness? Are the numbers and cost of each C&A known? Sometimes this attribute is eliminated from the estimate because the software does not require C&A.
| 5.0 System Facilities | This attribute addresses the hardware used to change, maintain, and test the software such as workstations, test facilities, and test equipment as well as keeping the lights on. Are the costs for hardware and utilities known? Sometimes this attributed is eliminated from the estimate because facility costs are covered by a different organization.
| 6.0 Sustaining Engineering | This attribute addresses costs associated with running a help desk, using a server hosting environment, engineering activities such as studies, design, test support, deployment, and training. For costs that are germane to the estimate, are the costs known?
| 7.0 Field Software Engineering | This attribute addresses on-site or field technical assistance, problem troubleshooting, software installation, operational assistance, and training. Are the costs for this service known?
| 8. Other Costs | This attribute address organizational costs usually in the form of a tax. Are these costs known?
Software Internal Attributes | External Interfaces | This attribute addresses the number of interfaces to other systems. The uncertainty is the unforeseen changes in an interface causing unplanned software changes. How many external interfaces are there and who owns the interfaces? What is the percentage of system data received and/or passed to other systems?
| Execution Timing Constraints | This attribute addresses the percentage of system key performance parameters that are dependent on real-time execution. Real-time software is challenging to sustain because of the need for guaranteed execution times, e.g., a flight controller that misses a cycle may lead to an uncontrollable air vehicle. What percentage of system key performance parameters depend on non-stop processing?
| COTS Product Incorporation | This attribute addresses the percentage of system key performance parameters met by COTS software. What percentage of the system functionality depends on COTS software?
| Critical Technology | This attribute addresses the software technology readiness level required to meet system key performance parameters. What percentage of software system components in use are approaching obsolescence? What is the complexity resulting from security or legal mandates?
| Data Rights | Often overlooked, this attribute addresses the rights, including copyright and other intellectual property, the program/project has to the technical data and computer software delivered as part of a contract. What is the extent of the program’s or project’s various license rights (e.g., unlimited, restricted, or limited)? Does (non)access to data rights affect the long-term cost of sustainment/maintenance?
Program / Project Management Attributes | Management Personal Capability | This attribute addresses the capability of management personnel. What percent of management is moderately to highly experienced in software maintenance? What percent of management has worked on this type of system before?
| Technical Personal Capability | This attribute addresses the capability of technical personnel. What percent of the personnel is moderately to highly experienced in software maintenance? What percent of the personnel is moderately to highly experienced with this type of system?
| Technical Process Capability | This attribute looks at process capability. What percent of the maintenance processes are useful/effective? What percent of software trouble reports are traceable to process shortfalls?
| Facilities & Infrastructure Support | Unlike the System Facilities attribute in Cost Environment, this attribute speaks to the adequacy of facilities and infrastructure to get the work done. What percent of the support tools is considered useful? What percent of needed planned capital equipment (e.g., for SILs, simulators, and emulators) is available?
| Sustainment / Funding Rhythm | This attribute looks at what drives software maintenance. What percent of the maintenance work is discretionary as opposed to legally mandated? What percent of funding has been changed in the past fiscal year? What percent of current maintenance work is attributed to backlog? What percent of current maintenance work is attributed to technical debt?
| Project & Program Management | This attribute looks at the stability of the management team. How experienced is the project/program management? Is the project/program management team stable or changing?
Eternal Program Environment Attributes | External Stakeholders | This attribute addresses the chaotic impact external stakeholders can have on a project. How many external stakeholders are there? Do external stakeholders provide funding, set requirements, or both? Is there agreement or conflict among different stakeholders as to the system’s mission priorities?
| Mandates | This attribute looks at the impact of non-negotiable requirements. How stable are mandated policies and guidelines and do they conflict? Are mandated policies, like security, fully funded?
| Policy-driven Sustainment / Funding Rhythm | This attribute addresses the impact of funding shortfalls and unfunded plans. How long does the project/program funding stream look secure? Are there planned and funded system upgrades?